## DOX EXE AS BUILT
ANNEXE : DOCUMENTS EXECUTION et AS BUILT Nom du projet : XXX Chantier : XXXX/XXXX/XX/XX
Le dossier As Built est compilé et transmis par l'adjudicataire. Les détails développés par l'adjudicataire doivent être mis en contexte en figurant les éléments connexes. Tous les plans sont à fournir aux formats pdf et dwg. Les fiches techniques devront contenir le contact du fabricant/fournisseur et le délai de garantie du produit |  |  |  | EXECUTION |  |  |  | AS BUILT
Auteur du Doc | CATEGORIE | SOUS-CATEGORIE | Détails des éléments à transmettre ( à compléter par les BE) | Echantillon / Moke up | Digital | Papier | Exemplaires | Digital | Papier | Exemplaires
EG/ENT | PREPARATION | Plans et documents démarrage chantier | Plan d'installations de chantier, Osiris etc |  | X
EG/ENT | PREPARATION | Sondages et relevés | Essais de sols complémentaires, pollution, amiante, relevés de situation existante, relevé impétrants |  | X |  |  | X
EG/ENT | PREPARATION | Etat des lieux ( avant/après) |  |  | X |  |  | X
EG/ENT | SUIVI CHANTIER | Sous-traitants , liste par métiers | [5 empty] | X
EG/ENT | SUIVI CHANTIER | Traitements des terres | Rapports, PV, certificats , relevés |  | X |  |  | X
EG/ENT | SUIVI CHANTIER | Traitement amiante | Rapports, PV, certificats , relevés |  | X |  |  | X
EG/ENT | ARCHITECTURE | Table des matières et listing détaillé | [5 empty] | X
EG/ENT | ARCHITECTURE | Plans et détails d'exécution | Menuiseries intérieures, menuiseries extérieures, calepinage |  | X |  |  | X
EG/ENT | ARCHITECTURE | Fiches techniques |  |  | X |  |  | X
EG/ENT | ARCHITECTURE | Notes de calculs et essais | Menuiseries extérierues, ferronerie |  | X |  |  | X
EG/ENT | ARCHITECTURE | Attestations | Rapports, PV, certificats, contrôle incendie |  |  |  |  | X
EG/ENT | ARCHITECTURE | Réemploi | Inventaire quantifié des matériaux démontés et stockés pour réemploi |  | X |  |  | X
EG/ENT | ARCHITECTURE | Echantillons et Moke up | Moke up parte de façade, quincailleries | X
EG/ENT | ARCHITECTURE | Notices, mode emploi, manuels entretien | Toiture verte, menuiseries ,plantations, ferroneries |  |  |  |  | X
EG/ENT | STABILITE | Table des matières et listing détaillé | [5 empty] | X
EG/ENT | STABILITE | Plans et détails d'exécution | Elements préfabriques : escaliers, balcons, corniches, prédalles, etc |  | X |  |  | X
EG/ENT | STABILITE | Fiches techniques |  |  | X |  |  | X
EG/ENT | STABILITE | Notes de calculs et essais | Elements préfabriqués, essai béton |  | X |  |  | X
EG/ENT | STABILITE | Attestations | Rapports, PV, certificats, contrôle incendie |  | X |  |  | X
EG/ENT | STABILITE | Echantillons et Moke up | Béton architectonique | X
EG/ENT | TS - HVAC | Table des matières et listing détaillé | [5 empty] | X
EG/ENT | TS - HVAC | Plans et schémas d'exécution | Schéma de principe HVAC et régulation, plans de positionnement à tous les niveaux , plan chaufferie |  | X |  |  | X
EG/ENT | TS - HVAC | Fiches techniques |  |  | X |  |  | X
EG/ENT | TS - HVAC | Notes de calculs et essais | Calcul des débits |  | X |  |  | X
EG/ENT | TS - HVAC | Attestations | Rapports, PV, certificats, contrôle incendie, contrôle gaz |  |  |  |  | X
EG/ENT | TS - HVAC | Echantillons et Moke up | Bouches de ventilation, radiateurs, thermostats, vannes | X
EG/ENT | TS - HVAC | Notices, mode emploi, manuels entretien | Chaudières, régulations collectives, thermostat |  |  |  |  | X
EG/ENT | TS - SANITAIRE | Table des matières et listing détaillé | [5 empty] | X
EG/ENT | TS - SANITAIRE | Plans et schémas d'exécution | Schéma de principe (adduction, évacuation , adoucisseur), plans de positionnement à tous les niveaux , plan du réseau d'égouttage enterré et aérien (CV , pentes , drains, etc) |  | X |  |  | X
EG/ENT | TS - SANITAIRE | Fiches techniques | Robinets |  | X |  |  | X
EG/ENT | TS - SANITAIRE | Notes de calculs et essais | Calcul des débits |  | X |  |  | X
EG/ENT | TS - SANITAIRE | Attestations | Rapports, PV de mise sous pression |  |  |  |  | X
EG/ENT | TS - SANITAIRE | Echantillons et Moke up | Robinets | X
EG/ENT | TS - SANITAIRE | Notices, mode emploi, manuels entretien | Adoucisseur, pompes, robinetterie |  |  |  |  | X
EG/ENT | TS - ELECTRICITE | Table des matières et listing détaillé | [5 empty] | X
EG/ENT | TS - ELECTRICITE | Plans et schémas d'exécution | Schéma des tableaux , plans de positionnement et schémas unifilaires à tous les niveaux |  | X |  |  | X
EG/ENT | TS - ELECTRICITE | Fiches techniques |  |  | X |  |  | X
EG/ENT | TS - ELECTRICITE | Notes de calculs et essais | Eclairage , cabine haute tension |  | X |  |  | X
EG/ENT | TS - ELECTRICITE | Attestations | Certificats et contrôles |  |  |  |  | X
EG/ENT | TS - ELECTRICITE | Echantillons et Moke up | Luminaires | X
EG/ENT | TS - ELECTRICITE | Notices, mode emploi, manuels entretien | Luminaires |  |  |  |  | X
EG/ENT | TS - LEVAGE | Table des matières et listing détaillé | [5 empty] | X
EG/ENT | TS - LEVAGE | Plans et schémas d'exécution | Plans détaillé des installations ( cabanons, cabines, trémies etc) |  | X |  |  | X
EG/ENT | TS - LEVAGE | Fiches techniques |  |  | X |  |  | X
EG/ENT | TS - LEVAGE | Notes de calculs et essais | Etude des flux |  | X |  |  | X
EG/ENT | TS - LEVAGE | Attestations | Rapports, PV, certificats , contrôle incendie |  |  |  |  | X
EG/ENT | TS - LEVAGE | Echantillons et Moke up | Finition ascenseurs | X
EG/ENT | TS - LEVAGE | Notices, mode emploi, manuels entretien | Ascenseurs |  |  |  |  | X
EG/ENT | TS - CONTROLE ACCES | Table des matières et listing détaillé | [5 empty] | X
EG/ENT | TS - CONTROLE ACCES | Plans et schémas d'exécution | Schémas électriques et schémas contrôle accès, plans de positionnement à tous les niveaux |  | X |  |  | X
EG/ENT | TS - CONTROLE ACCES | Fiches techniques |  |  | X |  |  | X
EG/ENT | TS - CONTROLE ACCES | Attestations | Rapports, PV, certificats , contrôle incendie , contrôle ascenseurs |  |  |  |  | X
EG/ENT | TS - LEVAGE | Echantillons et Moke up | Finition ascenseurs | X
EG/ENT | TS - CONTROLE ACCES | Notices, mode emploi, manuels entretien | Système des badges, intratone |  |  |  |  | X
EG/ENT | TS - INCENDIE | Table des matières et listing détaillé | [5 empty] | X
EG/ENT | TS - INCENDIE | Plans et schémas d'exécution | Plans reprenant les moyens de détection et d'extinction (détection, sprinklage , déviroirs , extincteurs, signalétique), schémas des tabelaux liés à la détection incendie |  | X |  |  | X
EG/ENT | TS - INCENDIE | Fiches techniques |  |  | X |  |  | X
EG/ENT | TS - INCENDIE | Notes de calculs et essais | Calcul des débits |  | X |  |  | X
EG/ENT | TS - INCENDIE | Attestations | Rapports, PV, certificats , contrôle |  |  |  |  | X
EG/ENT | TS - INCENDIE | Echantillons et Moke up | Moke up armoires dévidoirs | X
EG/ENT | TS - INCENDIE | Notices, mode emploi, manuels entretien | Centrale de détections |  |  |  |  | X
EG/ENT | TS - IMPETRANTS | Table des matières et listing détaillé | [5 empty] | X
EG/ENT | TS - IMPETRANTS | Plans et schémas d'exécution |  |  | X |  |  | X
EG/ENT | TS - IMPETRANTS | Fiches techniques |  |  | X |  |  | X
EG/ENT | TS - IMPETRANTS | Attestations | Rapports, PV, certificats , relevés |  | X |  |  | X
AUTRES | ARCHITECTURE | PV de réunions de chantier | [5 empty] | X
AUTRES | ARCHITECTURE | Plans et détails de principe mis à jour par AR | [5 empty] | X
AUTRES | STABILITE | Plans et détails de principe mis à jour par la STAB | [5 empty] | X
AUTRES | TECHNIQUES SPECIALES | Plans et schémas de principe mis à jour par TS | [5 empty] | X
AUTRES | BUREAU DE CONTRÔLE | Rapports | [5 empty] | X
AUTRES | ACOUSTIQUE | Rapports | [5 empty] | X
AUTRES | CONSEILLER PEB | Attestation et rapport final | [5 empty] | X
AUTRES | COORDINATEUR SECURITE | Rapports | [5 empty] | X
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A compléter si nécessaire
Note on H3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A compléter si papier
Note on J3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A compléter si nécessaire
Note on K3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A compléter si papier
Note on B24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ventilation et Chauffage
Note on B25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ventilation et Chauffage
Note on B26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ventilation et Chauffage
Note on B27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ventilation et Chauffage
Note on B28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ventilation et Chauffage
Note on B30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ventilation et Chauffage
Note on B31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Adduction et évacuation des eaux , égouttage entérré appareils sanitaires
Note on B32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Adduction et évacuation des eaux , égouttage entérré appareils sanitaires
Note on B33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Adduction et évacuation des eaux , égouttage entérré appareils sanitaires
Note on B34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Adduction et évacuation des eaux , égouttage entérré appareils sanitaires
Note on B35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Adduction et évacuation des eaux , égouttage entérré appareils sanitaires
Note on B37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Adduction et évacuation des eaux , égouttage entérré appareils sanitaires
Note on B38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Electricité communs , éclairage secours logements , abords
Note on B39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Electricité communs , éclairage secours logements , abords
Note on B40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Electricité communs , éclairage secours logements , abords
Note on B41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Electricité communs , éclairage secours logements , abords
Note on B42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Electricité communs , éclairage secours logements , abords
Note on B44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Electricité communs , éclairage secours logements , abords
Note on B45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ascenseurs, monte-charges, plateforme PMR etc
Note on B46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ascenseurs, monte-charges, plateforme PMR etc
Note on B47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ascenseurs, monte-charges, plateforme PMR etc
Note on B48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ascenseurs, monte-charges, plateforme PMR etc
Note on B49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ascenseurs, monte-charges, plateforme PMR etc
Note on B51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ascenseurs, monte-charges, plateforme PMR etc
Note on B52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Parlophonie, badges, caméras, organigramme clés
Note on B53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Parlophonie, badges, caméras, organigramme clés
Note on B54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Parlophonie, badges, caméras, organigramme clés
Note on B55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Parlophonie, badges, caméras, organigramme clés
Note on B57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Parlophonie, badges, caméras, organigramme clés
Note on B58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: centrale incendie, détections, alarme, sprinklage , dévidoir, extincteur
Note on B59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: centrale incendie, détections, alarme, sprinklage , dévidoir, extincteur
Note on B60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: centrale incendie, détections, alarme, sprinklage , dévidoir, extincteur
Note on B61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: centrale incendie, détections, alarme, sprinklage , dévidoir, extincteur
Note on B62: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: centrale incendie, détections, alarme, sprinklage , dévidoir, extincteur
Note on B64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: centrale incendie, détections, alarme, sprinklage , dévidoir, extincteur
Note on B65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Raccordements aux régies, compteurs
Note on B66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Raccordements aux régies, compteurs
Note on B67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Raccordements aux régies, compteurs
Note on B68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Raccordements aux régies, compteurs